## Task List
[6 empty] | February | [6 empty] | ol | [30 empty] | April | [29 empty] | May
Requirement doc reference | Requirement | Task | Estimate | Actual Time Spent | Owner | 1900-01-24 | 25 | 2019-08-26 | 1900-01-26 | 27 | 2018-08-28 | 2018-08-29 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 1900-01-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16
| Environment Setup | Creating project in Github | 1 | 3
|  | Creating AWS account. |  |  | Sai
|  | Create Database and temp table and connect db with nodejs.(insert/query) | 2 |  | Sai/Prakhs
|  | System setup | 1 |  | All
| Setting up backend. | Creating all tables. | 1 |  | Kar
|  | Populate Dummy data | 1 |  | Kar
1,2,6,16 | Sign In/Sign Up Page | Email/Facebook | 2 |  | Suhash
| Common Layout |  | 2 |  | Sai
| User Home Screen | Changed this to have navigation to entertainer search and my events | 2 |  | Kar
7,8 | Entertainer Search | Search for Name, Sort for(rating,name,years worked,events completed),talent(card/filter) | 3 |  | Prakhs
9 | Events | Create Event/View event | 2 |  | Suhash
| Business | View Businesses | 2 |  | Kar
15 | Contact Us | Send email(complaint/feedback) | 2 |  | Prakhs
11,25,32 | Chat | Create. Delete after one week of event. | 3 |  | Sai/Suhash
5,19,29 | My account | My Events(listing/cancel) | 2 |  | Kar
3 |  | Edit Profile | 2 |  | Suhash
4,18,28 |  | Create Entertainer Profile | 2 |  | Sai
|  | Create Business Profile | 2 |  | Prakhs
22 |  | Edit Requirement form |  |  | Sai
10,11 | Proposal Form |  |  |  | Prakhs
35 | Admin account | Promote User | 2 |  | Prakhs
33,39 |  | Account Verification | 2 |  | Suhash
34 |  | View booked events | 2 |  | Sai
37 |  | Modify/ Add category | 2 |  | Prakhs
36,40 |  | View /Respond Complaints/Feedback | 2 |  | Sai
38 |  | Deactivate Accounts | 2 |  | Kar
|  | Cancel Events | 2 |  | Kar
12 | Payment | Stripe/Paypal---- Implementing stripe | 3 |  | Kar
12 |  | Refund | 2 |  | Kar
13,26 | Verification Push |  | 2 |  | Suhash
14 | Rating |  | 2 |  | Prakhs
| Unit Testing | For Each Component | 5 |  | Unassigned
| Integration Testing |  | 4 |  | Unassigned
17,20,21,23,24,30,31 | Email Notification |  | 2 |  | Prakhs
27 | Business Profile | View Entertainers | 2 |  | Kar
Karthika
Prakhathi
Sai Anand
Suhash